## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 28/09/2023 | 1. Determine the environment configuration 2. Determine the general content of the project 3. Assigned roles to all members 4. study python flask | NAH | 1.New members join | 1. Assign everyone’s iteration work All code work must be completed before 2.14/10. 14-18 Complete document work | 0 | 0 | 0 | 0 | 0 | 15 | 13 | 2 | 1 | 2 | 0.5 | 11.5
1 | 19/10/2023 | 1. Improved system design (4 modules) 2. Preliminarily implemented the functions of the user module (home page, menu, login, registration, shopping cart, confirmation page) 3. Preliminarily completed the database | 1. Failure to unify the database 2. The project functions need to be improved (blank lines on the registration page, adding dishes to calculate the total price, and returning to the confirmation page from multiple pages) | 1. Some students were unable to complete the task due to unexpected circumstances 2. The project requirements are not clear, resulting in imperfect functions of the final project. | 1. Iteration 1.5 was completed in the first week, the database was completed, and the various pages of the user module were connected in series. 2. Complete the waiter and kitchen modules in the second week 3. All projects must be updated on git every week for checking | 20 | 5 | 2 | 0 | 2 | 35 | 32 | 3 | 5 | 25 | 5
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## chandrasiri
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 07/09-13/09 | 5 | 5 | 0 | 0 - learn git and python, read several tutorials | 5 | - | - | - | - | - | - | - | - | Not familiar with Flask, Git with a group. Communication is not clear. Task assignments are not clear. Couldn't joint with a team | Go through online tutorials. | 0 - continue to learn git Python and Flask | 4
2 | 14/09-20/09 | 4 | 3.5 | 0.5 | 0 - learn Git and Python, Flask | 3.5 | - | - | - | - | - | - | - | - |  | Joined with team3. Finish some tutorials on Git. Get familiar with assignments and future tasks as well. | 0 - continue to learn Python and Flask | 6
3 | 21/09-27/09 | 7 | 7 | - | 0 - Learn Python, Flask 7 - Worked on SPPP Risk Mgt and SPP.docx | 1 | - | - | - | - | - | - | 2 | Works for ieration 0 * Prepare some parts of the presentation |  |  | 7 - Plan to support for the iteration1 and 0 - Learning Python and Flask | 8
4 | 28/09-03/10 | 8.5 | 8 | 0.5 | 0 - Learn Python, Flask, UML, Pivotal Tracker 1 - Create user stories and defines the EBC for the requirements of Menu pages. 2 - Create UML Class diagram for Menu management 3 - Prepare for iteration1, understand the work modules of the project, Create a basic Falsk pages 5 - communicate with the team leader after the weekly meeting and read the meeting record. 6-Troubleshoot PDE some environment compatibility and dependencies 7-Prepare the meeting minute | 3 | 0.5 | 0.5 | 2 | - | 0.5 | 1 | 0.5 |  | - PyCharm, SQLite, React,.. are new to me | Go through online tutorials and get hands-on experience with sample projects. | 3 - Plan to complete my task for the iteration-1 before the deadline. 0 - Continue learning Python with Flask and React | 8
5 | 04/10-11/10 | 8 | 4 | 0.5 | 0 - Learn Python, SqlAlchemy, Blueprints, UML 2 - Update the UML Class diagram for Menu management 3 - In order to start the menu module, setup the MVC like architechture for the project using Blueprint. 4 - Create unit tests for the requirements of Menu pages. 7-Prepare the meeting minute. Beautify (typography) the meeting minute and progress report. | 4 | - | 0.5 | 2 | 0.5 | 0.5 |  | 0.5 |  |  | Got familiar with PyCharm, SQLite, SQLAlchemy, ORM and Blueprint. |  | 8
6 | 12/10-18/10 | 10.5 | 1 |  | 0 - Learn Python 3 - Defined models for the menu project using the ORM. Defined and registered controllers using Blueprint. Defined CRUD operations using the ORM for the models on their controllers. Defined the HTML and CSS for the view pages. 4 - Completed unit tests on menu module for the iteration1. 5- Update team members about the status of the menu module tasks using Discord and Blackboard. 7-Prepare for presentation of the iteration 1 | 1 | - | - | 8 | 0.5 | 0.5 | - | 0.5 |  | -Need to be familiar with React. | Hope to go through online tutorials and get hands-on experience with sample React projects. |  | 8

## Jialin Li
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/14-09/21 | 7 | 6 | 1 | 0 - learn basic knowledge about git, flask 1 - analysis the project requirements with team members 5 - attend in teaming weekly meeting, make project plan, send reminders to team member with teammates 6 - set up git and complete lab1 7 - research similar products | 2 | 1 |  |  |  | 1 | 2 | 1 | 1.set up git and complete the lab1 task 2. analysis the project requirements | 1. It is my first time to learn the Flask, so it take me some time to be familiar with the Flask's basic options. 2. There are some problems with communication since the teammates are from different countries. | 1. Flask tutorials part 1 on progress 2. git commands tutorials on progress | 0 - continue to learn flask and git commands 1 - prepare for next iteration 2 - implement a basic code world with flask | 7
2 | 09/21-09/28 | 6 | 5 | 1 | 0 - keep studying in git and flask 1 - prerare for lteration 0 presentation 2 - (1）Participate the group meeting, (2) determined the QA content of the project， (3)finish all documents about iteration 0 3 - prepare for iteration 1 | 2 | 1 | 1 | 2 |  |  |  |  | 1. keep studying knowledge about git and flask 2. write the Quality Assurance Plan about Project Proposal and Planning 3. participate the presentation 0 | 1. Still not familiar enough with flask framework and python code | 1. keep watching python Flask tutorials | 0 - continue to learn flask and git deepen 1- prepare for iteration 1 | 7
3 | 09/28-10/05 | 7 | 6 | 1 | 0 - Add tasks in the Pivotaltracker 1 - analysis the entity, boundary and Control objects 2 - draw class diagram 3 - Clarify my work modules | 2 | 1 | 1 | 3 |  |  |  |  | 1.The requirements for the confirmation and feedback interfaces were successfully analyzed in the Pivotaltracker 2.The class diagram of the interface is improved to match the specific requirements | 1.The requirements analysis still needs to be perfected 2.There were certain aspects of the task that were not written in enough detail | 1.According to the actual situation of the implementation, the requirements are further improved 2.Think about what needs to be added to the details of the task and add it in time | 1.Start to build the basic code of the page, so that some functions can be realized 2. Modify the subsequent development tasks appropriately according to the actual development situation | 8
4 | 10/05-10/12 | 6 | 5 | 1 | 0 - Setting up the project development environment 1 - Finalizing the assignment of tasks for the project. 2 - Complete lab2 3 - Complete Quiz1 | 2 | 1 | 1 | 2 |  |  |  |  | 1. Successfully set up the project development environment 2. Complete the assignment successfully The project. 3. Completed experiment 2 4. Completed Quiz1 | 1. The specific environment configuration needs to be further improved by referring to the code | 1.In the code writing, constantly analyze the actual situation to improve 2.Correct problems when discovered | 1.Finalizing the assignment of tasks for the project 2.make SPPP paragraph updated | 7
5 | 10/12-10/19 | 7 | 6 | 1 | 0 - update the SPPP paragraph 1 - Carry out final completion of the project 2 - Log meeting minutes | 2 | 1 | 1 | 3 |  |  |  |  | 1. The SPPP paragraph updated 2. The final completion of the project finished 3. Meeting minutes loged | 1.The comments to the code are not particularly specific 2.The front end interface is not particularly beautiful | 1.Further refinement of code comments to make their meaning clearer 2.Further beautify the front-end interface | 1.Prepare requirements analysis for Iteration 2 2.Refine the project for Iteration 1 | 6

## Siyuan Xue
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/014-09/21 | 5 | 5 | 1 | 0 - study git and flask 1 - complete Meeting Minutes 2 - (1）Hosted the group meeting, (2)assigned week1 tasks to everyone, and determined the general content of the project，(3)Lead team members to familiarize themselves with the production of all documents 3 - lab 01(set up git) | 2.5 | 1 | 1 | 0.5 |  |  |  |  | 1 - Complete Meeting Minutes 2 - set up git for Siyuan part(lab01) 3 - (1）Hosted the group meeting, (2)assigned week1 tasks to everyone, and determined the general content of the project，(3)Lead team members to familiarize themselves with the production of all documents 4 - Assign weekly tasks to team members | 1 - Not familiar enough with flask 2 - Specific details of the project have yet to be determined | 1 - Flask tutorials part 1 on progress 2 - git commands tutorials on progress 3 - Preparing content for week2 meeting | 1 - Complete flask tutorials second part 2 - Determine members will deliver the presentation0 and content for presentation0 3 - Prepare content for week2 meeting | 7
2 | 09/21-09/28 | 6 | 5 | 1 | 0 - Prepare presentation0 1 - Find project-related information and determine project design content 2 - (1) Hosted the group meeting, (2) assigned week2 tasks (details in discord) | 2 | 3 | 1 | 6 |  |  |  |  | 1 - presentation0 overview_part 2 - Determine the project design content (details are in SPPP, overview&related part) 3 - (1) Hosted the group meeting, (2) assigned week2 tasks (details in discord) | 1 - presentation0 Poor oral expression 2 - Absence of key team members and major mistakes in presentation0 | 1 - End of preliminary learning of Flask 2 - Clarify the functions that the project needs to implement 3 - Clarify the tools for the project | 1 - Prepare for iteration 1 and weekly tasks 2 - Let the implementation leader assign everyone’s coding tasks 3 - Preparing for Iteration 1 PPT | 12
3 | 09/28-10/05 | 4 | 3 | 1 | 0- Create user stories 1- Determine future project functions 2- Assign members tasks 3- host a meeting | 1 | 1 | 1 | 1 |  |  |  |  | 1. Assist in designing future project features 2. Assign members tasks 3. host a meeting | N/A | N/A | 1. Iteratation1 code project | 10
4 | 10/05-10/12 | 13 | 12 | 1 | 1. Learn React Bootstrap and SQLite 2. Complete homepage design 3. host a meeting | 7 | 5 | 1 | [5 empty] | 1. Prepare for web design 2. Accelerate the development process | N/A | N/A | 1 iteration 1 project acceptance 2. Prepare speech | 20
5 | 10/12-10/19 | 21 | 20 | 1 | 1. Complete homepage code/testing 2. Prepare your speech 3. Complete the team leader’s related document tasks 4. Handle emergencies 5. host the meeting | 5 | 4 | 4 | 7 | 1 |  |  |  | 1. Complete homepage code/testing 2. Complete the presentation2 3. Complete the team leader’s related document tasks | 1. Teammates did not complete project tasks | 1. The team is making up for the unfinished tasks of teammates. | 1. Iteration 1.5 (concatenation of user interface pages) 2. Kitchen module, waiter module 3. Database construction | 20

## Xiankun Niu
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 6 | 5 | 1 | 0 - learn the basic knowledge of GitHub and Flask, preview the Module 1 Lecture 1 - analyze and determine the basic requirement of the project with my teammates 5 - have a online meeting on the discord and make the project plan together with my teammates 6 - set up Git and completed Lab1 task 7 - research similar products | 2 | 1 |  |  |  | 1 | 1.5 | 0.5 | 1. set up git and complete Lab1 2. research similar products and write a research report | 1. It is my first time to learn the Flask, so it take me some time to be familiar with the Flask. 2. There are some problems with communication since the teammates are from different countries. | 1. find and complete a set of Flask online turorial, master the basic konwledge of Flask. 2. use the text and screenshots to solve the communication problems. | 0 - continue to learn Flask 1 - complete the feasibility analysis of the project 5 - set up the project schedule with teammates 6 - Configure the environment for Flask in Pycharm and create a Flask Project. | 7
2 | 09/21-09/28 | 7 | 7 | 0 | 0 - continue to learn Github and Flask, read some source code and lecture about Flask structure 1 - write the management plan part of SPPP and prepare for presentation 0 2 - preview the Module 2 Lecture, the design part 5 - communicate with the team leader after weekly meeting and read the meeting record 7 - learn how to draw UML | 3 | 2 | 0.5 |  |  | 0.5 |  | 1 | 1. complete the Management Plan part of SPPP 2. prepare for the presentation 0 and complete the project objectives and priorities part of PPT 3. complete the weekly ProgressReport | 1. be absent from presentation 0 because of having a fever 2. be absent from week 2 meeting since I was out for a dinner 3. have difficulty in read the source code of Flask Structure | 1. ask for the team leader's help and I will attend presentation 1 2. read the meeting report after the week 2 meeting 3. find some lecture about the source code and truly understand it | 0 - proceed to learn Flask 2 - come to design the structure of the project and write some code of Flask 3 - learn the Design part of Module 2 4 - prepare for the Iteration 1 with my teammates 7 - complete Lab2 assignment | 8
3 | 09/28-10/05 | 9 | 6.5 | 1.5 | 0 - Continue to learn Flask and watch some tutorials for React Framework 1 - Revise and improve SPPP project documentation 2 - design the architecture of the project and user class 3 - create a basic flask page (need further development) 5 - discuss the shortcoming of presentation0 and clarify the coding assignments of Iteration1 6 - unify the development environment with teammates 7 - discuss the innovation of our project with teammates | 3 | 0.5 | 1 | 1.5 |  | 1.5 | 1 | 0.5 | 1. complete Lab2 2. complete week3 meetingminutes 3. complete the weekly ProgressReport 4. clarify the coding assignment of Iteration1 for teammates 5. explain the communiciation and relation among the system roles (manager, customer, server, kitchen) | 1. our project doesn't have innovation so far 2. coding part hasn't started 3. run into a dilemma about the configuration：too expensive all on the cloud & maybe inconsistent with others | 1. figure out some ideas: QR code intergration and recommend dished by invoke chatGPT API 2. assign Iteration1 task for teammates 3. unify the development environment with teammates and make the integration tests and deploy the database on the cloudfare | 0 - proceed to learn the Flask and React 2 - design the classes involved to login webpage 3 - code and finish login page 5 - communicate with teammate about the process of project | 12
4 | 10/05-10/12 | 12 | 11.5 | 0.5 | 0 - learn Flask and React Bootstrap 2 - design and implement the classes involved to login webpage 3 - create the login page 5 - discuss and decide the database to use, clarify everyone's task 6 - setup the SDE(Pycharm) | 2 | 8 | 1 |  |  | 0.5 | 0.5 |  | 1. complete the project flowchart 2. complete the login webpage and push it to Github | N/A | N/A | 0 - learn Module 3 and continue to learn Flask and React Bootstrap 3 - merge and connect everyone's pages 5 - prepare for Iteration 1 7 - write SDD document | 10
5 | 10/12 - 10/19 | 18 | 17.5 | 0.5 | 0 - learn Flask SQLALchemy and React Bootstrap 1 - update the SPPP document and finish the SDD document 2 - design the database with Tony and Siyuan 3 - complete the loginpage, merge for iteration 1 4 - test the merged project 5 - communicate the debug and deployment problems while testing | 3 | 2 | 1 |  | 8 | 2.5 | 1 |  | 1. update the SPPP document and finish my part of SDD document 2. finish the loginpage 3. merge and test for Iteration1 | 1. unexpected computer breakdown problem and did not push the project to Git in time | 1. communicate with the teamleader Siyuan and with the help of Tony, finally complete the basic version. And I will make up for this in the next Iteration2. | 0 - continue to learn Module 3 and Flask 2- database constuction and connect 7 - prepare for Iteration 2 | 16

## Zhuoru Song
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/14-09/21 | 6 | 4 | 2 | 0 - learn git 5 - Project planning with teammate 6 - Set up git | 2 |  |  |  |  | 2 | 2 |  | Set up git and update readme file | No significant issues found in this week | No significant issues found in this week | 0 - Start learning flask 1 - Start SPPP | 6
2 | 09/21-09/28 | 10 | 9 | 1 | 0 - learn flask and UML 1 - Propos High level Requirements in SPPP 3 - SPPP documentation 5 - Team meeting | 5 | 3 | 1 |  |  | 1 |  |  | Finish the Proposed High level Requirements part in SPPP | Not familar with flask start learning from zero | Keep learning step by step | 0 - Keep learning flask 1 - Add user story in lab | 10
3 | 09/28-10/05 | 13 | 13 | 0 | 0 - learn flask 1 - Add user story 4 - Add acceptance tests for user storys | 7 | 3 |  |  | 3 |  |  |  | Add user storys and for each user story give a acceptance test | 1. flask still hard to learn 2. User story written by different maybe have conflict in the content | 1. Try a simple flask web page 2. Find conflicts and communicate with other team members | 0 - Learn needed tools for the implementation 3 - Start implementation | 13
4 | 10/05-10/12 | 12 | 11 | 1 | 0 - learn Sqlite, flask, pycharm 3 - Start project. Add templates 5 - Job distribution 6 - Config local working environment | 6 |  |  | 3 |  | 1 | 2 |  | Coding for cart page | No significant issues found in this week | No significant issues found in this week | 0 - learn flask 2 - SDD 3 - finish cart page coding | 12
5 | 10/12-10/19 | 20 | 19 | 1 | 0 - learn flask 2 - Do the Design Patterns part in SDD 3 - Coding for cart page 5 - communicate with teammate for database detiles | 8 |  | 3 | 8 |  | 1 |  |  | 1. Write Design Patterns part in SDD 2. Coding for cart page 3. Participate in Iteration 1 presentation | 1. Spent very long time to study and have to frequently stop and student new content. 2. Sometimes the work to do is based on other team members work | communicate with other team member more frequently and have backup plans if there are some member are not available | 0 - learn flask 3 - link cart page to DB | 20

## Tony Xiang
Your Lead Roles: Config Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | N/A due to team redistribution.
2 | 09/21-09/28 | 5hr | 4hr | 1hr | 0 - Learning Flask 2 - SPPP config part 5 - Role discussion 6 - Web app implementation research | 1hr |  | 1hr |  |  | 1hr | 2hr |  | Implementation structure research. Make sure variety of IDE won’t affect workflow. Ability to understand basic Flask. | N/A | N/A | Learn Flask Hosting solution research. Database solution research. Git branching strategy explanation. | 5hr
3 | 09/29-10/5 | 6hr | 5hr | 1hr | 0-Potnetial service usage 1- Create User stories 5-Coding responsibility assignment 6- Create file structure for iteration 1 | 3hr | 1hr |  |  |  | 1hr | 1hr |  | Create development flow. Help design software. | N/A | N/A | Set up standard dev enviroment. Develop Registration page. Set up git commit stratagy. | 10hr
4 | 10/6-10/12 | 7hr | 6hr | 1hr | 0 - Learn Pyrebase 3- Design front end 6- Establish IDE standards | 2hr |  |  | 3hr |  |  | 2hr |  | Prepare for security sign on Accelerate dev process | N/A | N/A | Create Sign up page and database | 7hr
5 | 10/13-10/19 | 9hr | 9hr | 0hr | 2 - Database Design 3 - Create Signup Page 3 - Initial merge for iteration 1 6 - Create main DB |  |  | 2hr | 6hr |  |  | 1hr |  | Merge for iteration 1 Create main database for all future dev | Short notice on merge | Basic version created. | Distribute database to all, stablize iteration 1 | 10hr
6